## Workflow Templates
THE CASE FOR GROWTH
thecaseforgrowth.com
CLIENT INTAKE WORKFLOW
Step | Action | Responsible | Timeline | Checklist
1 | Initial consultation completed | Attorney | Day 0 | Conflicts check done
2 | Send engagement letter | Paralegal | Day 1 | Client info collected
3 | Receive signed letter + retainer | Admin | Day 3-5 | Payment processed
4 | Welcome email sent | Attorney | Day 6 | Next steps outlined
5 | Open case in system | Paralegal | Day 6 | Calendar dates set
6 | Kickoff call scheduled | Attorney | Day 7-10 | Strategy discussed

## Discovery Workflow
DISCOVERY PHASE WORKFLOW
Step | Action | Responsible | Timeline | Checklist
1 | Discovery plan created | Attorney | Week 1 | Scope defined
2 | Requests drafted | Paralegal | Week 2 | Reviewed by attorney
3 | Requests served | Admin | Week 3 | Proof of service filed
4 | Responses reviewed | Attorney | Week 7-8 | Follow-up identified
5 | Depositions scheduled | Paralegal | Week 9 | Witnesses confirmed
6 | Discovery closed | Attorney | Week 12 | Summary prepared

## Case Closing Workflow
CASE CLOSING WORKFLOW
Step | Action | Responsible | Timeline | Checklist
1 | Final settlement/judgment | Attorney | Day 0 | Terms confirmed
2 | Close case in system | Paralegal | Day 1 | Notes finalized
3 | Final bill sent | Admin | Day 3 | Balance calculated
4 | Files organized/archived | Paralegal | Day 7 | Digital backup done
5 | Closing letter sent | Attorney | Day 10 | Review requested
6 | Follow-up call | Attorney | Day 30 | Satisfaction confirmed